## Summary
DecisionOS — Development Estimate
Project | DecisionOS | Prepared | June 2026 | Version 1.1
Client | Confidential | Delivery Model | AI-Assisted (Claude Code SDD) | Status Draft
KEY METRICS
Total Scope (AI-Assisted) | ~69.5 days
Traditional Equivalent | ~163 days
AI Speed Advantage | ~2.4× faster
3–4 Week Delivery (parallel) | YES
Infra Cost at Launch | $0/month (client's server)
PHASE BREAKDOWN SUMMARY
Phase | Description | AI Days | Traditional Days | Status
Phase 0 | Frontend Prototype (complete) | Done | — | ✅ Complete
Phase 1 | Backend Foundation (Postgres + Auth + schema-per-tenant) | 7.5 | 20 | Pending
Phase 2 | File Ingestion (R2 + CSV/Excel parser) | 6.5 | 15 | Pending
Phase 3 | Data Connectors (Zoho + Custom ERP + PgSQL) | 13 | 28 | Pending
Phase 4 | AI / LLM Engine (RAG + 7-agent + streaming) | 21 | 51 | Pending
Phase 5 | Frontend Integration + Subscription Enforcement | 9.5 | 21 | Pending
Phase 6 | Production Hardening (security + perf) | 5 | 14 | Pending
Phase 7 | QA, CI/CD & Deployment | 6.5 | 15 | Pending
TOTAL |  | ~69.5 | ~163
INFRASTRUCTURE COSTS (MONTHLY AT LAUNCH)
Service | Purpose | Plan | Monthly Cost
Next.js app | Frontend + API Routes (Docker + Nginx) | Client's server | $0
PostgreSQL + pgvector | DB + pgvector + schema-per-tenant | Self-hosted | $0
Redis | Rate limiting + AI response cache | Self-hosted | $0
Local disk | File storage — CSV, Excel, ERP exports | Client's server | $0
Sentry | Error monitoring | Developer (free) | $0
GitHub | Source control + CI/CD (SSH deploy) | Free | $0
TOTAL |  |  | $0/month

## Detailed Estimate
DecisionOS — Detailed Phase Estimate
All figures are AI-assisted (Claude Code SDD). Traditional equivalent shown for comparison.
Phase | Task / Deliverable | AI Estimate | Traditional | Priority | Notes
Phase 1 — Backend Foundation
| PostgreSQL schema (all 7 table groups: identity, data, BI, AI/chat, decisions, workflow, governance) | 2 days | 4 days | Critical | Drizzle ORM + self-hosted Postgres
| Self-hosted Postgres setup + pgvector extension + Drizzle migrations | 0.5 day | 2 days | Critical | Runs on client's server
| Auth.js v5 — Credentials + bcrypt + JWT (httpOnly cookie, 7-day) | 1 day | 4 days | Critical
| Session middleware (JWT validation on every API route) | 0.5 day | 2 days | Critical
| Schema-per-tenant middleware (search_path per connection) | 2 days | 4 days | Critical | Complete tenant isolation at DB level
| Next.js API Routes scaffold (versioned, Zod-typed) | 1 day | 3 days | Critical
| Zustand auth store → real JWT session (replace mock cookie) | 0.5 day | 1 day | Critical
Phase 1 Total |  | 7.5 days | 20 days
Phase 2 — File Ingestion Pipeline
| File upload endpoint (multipart → local disk, served via Nginx static path) | 1 day | 3 days | High
| CSV parser (Papa Parse) + Excel parser (xlsx library) | 1 day | 2 days | High
| Schema inference (auto-detect column names + data types) | 2 days | 4 days | High
| Data normalisation → typed Postgres tables per source (dynamic DDL) | 1 day | 3 days | High
| Upload wizard → real API integration (existing frontend) | 1 day | 2 days | High
| Ingestion history logging | 0.5 day | 1 day | Medium
Phase 2 Total |  | 6.5 days | 15 days
Phase 3 — Data Connectors
| Zoho CRM — OAuth 2.0, REST API v7, Contacts/Deals/Accounts sync, delta sync via Modified_Time | 4 days | 8 days | Launch | Client to register Zoho Server App
| Custom ERP — Generic REST adapter, configurable auth, field mapping UI, webhook receiver | 4 days | 9 days | Launch | Client to share API docs
| PostgreSQL direct — connection config, table browser, scheduled SELECT pull | 2 days | 4 days | Launch
| Sync scheduler — pg-boss job queue, cron per source, retry + exponential backoff | 2 days | 5 days | Launch
| Connector UI wiring — OAuth redirect → callback → encrypted credential storage (AES-256-GCM) | 1 day | 2 days | Launch
| Google Sheets connector (OAuth + Sheets API v4) | 2 days | 4 days | Post-launch | Sprint 2
| Salesforce connector (OAuth 2.0 PKCE + SOQL) | 3 days | 7 days | Post-launch | Sprint 2
Phase 3 Total (Launch) |  | 13 days | 28 days |  | Post-launch: +5 days
Phase 4 — AI / LLM Engine
| pgvector extension + embedding schema | 0.5 day | 2 days | Critical
| Embedding pipeline — chunk rows → embed via provider → store vectors | 2 days | 5 days | Critical
| RAG retrieval — query → embed → cosine similarity → context assembly | 2 days | 6 days | Critical
| SQL generation — LLM → SQL → AST safety check (SELECT-only) → execute → citations | 2 days | 5 days | Critical | node-sql-parser prevents writes
| Multi-provider LLM router — routes to tenant's configured provider | 2 days | 4 days | Critical
| LLM provider integrations: Anthropic Claude, OpenAI GPT-4o, Google Gemini | 2 days | 5 days | Critical | Tenant supplies own API keys
| LLM Connect wizard — provider selector → paste API key → test connection → save default | 1 day | 2 days | High | Simple, wizard-style UX
| LLM usage logging — llm_usage_logs table (tokens, cost_estimate, provider, user) | 0.5 day | 1 day | High | Foundation for usage dashboard
| 7-agent orchestration — Intent → Governance (PII masking) → Data Analyst → BI → Insight → Recommendation → Workflow | 4 days | 9 days | Critical | Strong model for analyst/insight/rec; fast for intent/gov/bi/workflow
| Chat session persistence — chat_sessions + chat_messages CRUD API, session list, pagination | 1 day | 2 days | Critical | Feeds session sidebar
| SSE streaming — AI response streams token-by-token to chat UI | 1 day | 2 days | Critical
| AI Executive Summary generator — nightly BullMQ cron per tenant | 1 day | 3 days | Medium
| Insight + Recommendation auto-generation (LLM + threshold rule engine, 4h cron) | 2 days | 5 days | High
Phase 4 Total |  | 21 days | 51 days
Phase 5 — Frontend Integration + Subscription Enforcement
| TanStack Query hooks for all endpoints (users, KPIs, insights, recommendations, tasks) | 2 days | 4 days | Critical
| Real KPI computation (SQL aggregates per tenant, configurable formulas) | 2 days | 4 days | High
| Real dashboard charts (live data → Recharts via API) | 1 day | 2 days | High
| Notification system (SSE endpoint → existing notification bell) | 1 day | 2 days | Medium
| Workflow / task CRUD persistence | 1 day | 2 days | Medium
| Subscription enforcement middleware — user + data source limits → 402 on breach | 1 day | 3 days | High | No query cap — tenant pays their own LLM
| Tenant Admin Console — LLM wizard + usage dashboard (tokens, cost estimate, per-user) | 1 day | 2 days | High
| Platform Admin panel — plan CRUD, per-tenant plan assignment | 0.5 day | 1 day | High
Phase 5 Total |  | 9.5 days | 20 days
Phase 6 — Production Hardening
| API rate limiting (self-hosted Redis sliding window, per user + per tenant) | 1 day | 2 days | High
| Error boundaries + structured logging (Sentry + Pino) | 1 day | 2 days | High
| Query result caching (self-hosted Redis, 5-min TTL for repeated AI queries) | 1 day | 3 days | Medium
| Security audit — SQL injection, XSS, OWASP headers, CSRF | 1 day | 3 days | High
| Multi-tenant data isolation audit — cross-tenant pen-test | 0.5 day | 3 days | Critical
| Password policy + account lockout | 0.5 day | 1 day | High
Phase 6 Total |  | 5 days | 14 days
Phase 7 — QA, CI/CD & Deployment
| Unit + integration tests (Vitest — API routes, auth, data ingestion, LLM router) | 2 days | 5 days | High
| E2E tests (Playwright — login, upload CSV, Zoho connect, ask AI, workflow create) | 2 days | 5 days | High
| GitHub Actions CI pipeline (type-check + lint + Vitest + Playwright + SSH deploy on merge) | 1 day | 2 days | High
| Production environment setup (Docker Compose + Nginx + self-hosted Postgres + Redis on client's server) | 0.5 day | 1 day | Critical
| Custom domain + SSL (Let's Encrypt via Certbot + Nginx) + env var management | 0.5 day | 1 day | High | Nginx handles SSL termination
| DB migration strategy (Drizzle migrate on deploy, zero-downtime) | 0.5 day | 1 day | High
Phase 7 Total |  | 6.5 days | 15 days
GRAND TOTAL | All Phases (1–7) | ~69.5 days | ~163 days |  | Wall-clock: ~3–4 weeks with parallelism

## 3-4 Week Delivery
DecisionOS — 3–4 Week Delivery Plan
5 parallel Claude Code SDD agent streams running simultaneously. 69.5 sequential days ÷ ~4.5 avg streams ≈ 15 effective days + buffer = 3–4 weeks.
Week | Stream A | Stream B | Stream C | Stream D | Stream E
Week 1 Foundation | Phase 1: PostgreSQL schema (all 7 table groups) + Drizzle ORM + self-hosted Postgres | Phase 1: Auth.js v5 + bcrypt + JWT + httpOnly cookie | Phase 1: Schema-per-tenant middleware + Zod API scaffold | Phase 7: CI/CD pipeline (GitHub Actions, Docker + SSH deploy, Nginx + Let's Encrypt) | Phase 2: File upload + local disk storage + Nginx static path
Week 2 Core AI | Phase 4: pgvector + embedding pipeline + OpenAI + Anthropic LLM adapters | Phase 4: RAG retrieval + SQL generation + chat sessions API | Phase 3: Zoho CRM OAuth + data sync + encrypted credentials | Phase 2: CSV/Excel parser + schema inference + dynamic DDL | Phase 5: TanStack hooks for Phase 1 endpoints (users, KPIs, dashboard)
Week 3 Full AI + Admin | Phase 4: 7-agent orchestration pipeline + SSE streaming | Phase 4: LLM connect wizard + usage logging + AI exec summary | Phase 5: Subscription enforcement + Tenant Admin (LLM + usage) + Platform Admin | Phase 3: Custom ERP connector + pg-boss sync scheduler | Phase 6: Redis rate limiting + Sentry + Redis query cache
Week 4 QA + Deploy | Phase 4: Insight + Recommendation auto-generation (cron) | Phase 5: Real charts + notification system + workflow persistence | Phase 7: Vitest unit + integration tests | Phase 7: Playwright E2E + production deploy (Docker + Nginx + Postgres + Redis on client server) | Phase 6: Security audit + data isolation pen-test + hardening
END-OF-WEEK CHECKPOINTS
Week | Milestone | Key Deliverables
Week 1 | Foundation Live | Real login + self-hosted Postgres live + file upload to local disk + CI/CD pipeline running
Week 2 | Core Value Prop Working | Upload CSV → Ask AI answers from it · Zoho CRM syncing · Dashboard KPIs live
Week 3 | Full AI + All Connectors | 7-agent AI chain + SSE streaming · All connectors live · Admin consoles · Rate limiting
Week 4 | Production Deployed | Production URL + custom domain · Playwright E2E passing · Security audit clean

## Subscription Plans
DecisionOS — Subscription Plans
Tenants bring their own LLM API keys and pay the LLM provider directly. Plans gate integrations + platform limits.
Feature | Trial | Starter | Professional | Enterprise
Price / month | $0 | $199 | $599 | $1,199
Users | 3 | 10 | 25 | Unlimited
Data Sources | 1 | 3 | 6 | Unlimited
AI Query Cap | No cap * | No cap * | No cap * | No cap *
OpenAI GPT-4o-mini | ✅ | ✅ | ✅ | ✅
OpenAI GPT-4o | ❌ | ✅ | ✅ | ✅
Anthropic Claude Haiku | ❌ | ✅ | ✅ | ✅
Anthropic Claude Sonnet | ❌ | ❌ | ✅ | ✅
Google Gemini Pro | ❌ | ❌ | ✅ | ✅
Ollama (self-hosted) | ❌ | ❌ | ❌ | ✅
Custom model endpoints | ❌ | ❌ | ❌ | ✅
LLM Usage Dashboard | ✅ | ✅ | ✅ | ✅
Zoho CRM connector | ✅ | ✅ | ✅ | ✅
Custom ERP connector | ✅ | ✅ | ✅ | ✅
Dashboards + KPIs | ✅ | ✅ | ✅ | ✅
AI Insights + Recs | ✅ | ✅ | ✅ | ✅
Workflows + Approvals | ✅ | ✅ | ✅ | ✅
Support | Community | Email | Priority Email | Dedicated
* No query cap enforced by DecisionOS — tenants pay their LLM provider directly for token usage.

## Open Items
Open Items & Client Dependencies
Item / Dependency | Detail | Owner | Risk if Delayed
✅ ANSWERED
LLM API key model | Tenants bring their own keys and pay the LLM provider directly. DecisionOS does not hold a shared key. | Confirmed | —
Delivery target | 3–4 weeks via parallel Claude Code SDD agent streams (5 streams at peak). | Confirmed | —
⚠️ PENDING — CLIENT ACTION REQUIRED
Custom ERP API documentation | Share base URL, auth type (API key / Bearer / Basic), and key endpoint schemas. Without docs, ERP connector cannot be scoped. | Client | HIGH — ERP connector deferred to sprint 2
Zoho app registration | Register a Server-based App in Zoho Developer Console (free). Share client_id + client_secret by Day 3. | Client | MEDIUM — Zoho sync delayed
Tenant LLM API keys for testing | Share an OpenAI or Anthropic API key for end-to-end testing of Ask AI. Required by start of Week 2. | Client | MEDIUM — AI testing blocked
DNS access for custom domain | Point your domain's A record to the client server's IP address. We will provide the IP once the server is set up. | Client | LOW — Custom domain delayed
❓ OPEN QUESTIONS
Number of launch tenants | How many tenant organisations at go-live? Informs connection pool sizing on the self-hosted Postgres instance. | Client | LOW
Zoho plan tier | Free plan = 100 API req/min; Professional+ = higher limits. Affects delta sync frequency. | Client | LOW — impacts sync frequency only
Post-launch: Stripe billing | Self-serve plan upgrade / downgrade via Stripe (~3 days). Confirm if needed in sprint 2. | Client | LOW